## Project Timeline
Amp Blog Implimentation
PROJECT DETAILS
DATE | MILESTONE | POSITION | BASELINE
2017-06-06 | Project Start | 25 | 1
2017-06-07 | Create Roadmap | 10 | 1
2017-06-09 | Setup STG & WP | -10 | 1
2017-06-16 | Duplicate blog to STG | 15 | 1
2017-06-20 | impliment Amp plug-ins & test for blog | 15 | 1
2017-06-22 | Update Shannon and ED on blog and valentens day | 15 | 1
2017-06-22 | Define system to rollout new content updates for AMP pages | -20 | 1
2017-06-22 | Update Shannon and ED on blog and valentens day | -15 | 1
2017-06-28 | shannon choose blog theme, research yoast |  | 1
2017-06-29 | matt finish content page for review, research meta data amp |  | 1
2017-07-06 | fix any addintion content page edits, submit for review |  | 1
2017-07-07 | impliment new blog theme with content, install AMP |  | 1
1
1
1
2017-07-15 | Finish Amp Blog | 15 | 1